## By People
Made by: | Standuply.com | For to-dos: https://trello.com/invite/b/WOnpFvhz/47e92133cc120bfb7fab93c12af3da9c/agile-unity-platformer
Person | Question | Week: <date>
|  | Monday | Tuesday | Wednesday | Thursday | Friday
Sprint 1 Learn Unity and make graphics | What did you do yesterday? | N/A | Realised how hard Unity is and decided to add to the goal, to learn Unity. Followed a tutorial to get started | Learned more Unity, made a basic contruct of what the game should be like. | Made edge detection and enemy destroying the player | Made main menu, but it doesn't have interactive buttons or background audio
| What will you work on today? | I will be learning the basics of Unity. I will also try to brainstorm the aspects of the game like characters, the goal of the game, enemy, main character, the concept. | Learn more of Unity of understand how the game making process works, also plan out a to-do list of what is needed for the project | Planned to ask Mr. Lee if we can take graphics from the internet. Prepare for the interview, learn more Unity, solify the foundation of the game. | Not that much time so make main menu | Brainstorm about the different players, enemies, and platforms/ground that can be made.
| Do you have any obstacles? | Know a bit of C#, but don't know how the Unity game engine works and how hard it is. Also never made a game before so I don't know what is need graphically and skills wise | Learning Unity is taking up a lot of time and still don't know really the game making process, also don't really know how to do character/background/graphical desgin that well | The learning process is taking longer than expected, so might have to work on the project during the weekend. Don't know how to make good levels, so the options are endless or take "inspiration from other games." | Different from what is done before | Have not played many platformes recently, so don't know what common enemies and ablilties are.
Sprint 2 | What did you do yesterday? | Researched what the players, enemies needed to be added: Player: 1 that dashs and 1 that glides. Enemies: add smart enemies with AI, and environmental enemies | Learn the basics of Unity. Learning how to implement that to characters, and enemies | Learned the theory behind adding gliding and dashingi in Unity and have a plan to implement that into the game. | Added collectors to the game, and turns out they weren't that hard to make | Added gldingin and dashing to the players. Plan to show Mr.Lee
| What will you work on today? | Learn the basics of inheritance, as it is quite different from java. | Research the theory behind how to make characters glide or dash. | Add a collector at the edge of the map to destory both players and enemies that fall of the edge. | Adding the gliding and dashing abilities, 1 to each player.. | Add the reset and home buttons, so that when the player dies they can start over.And the home buttons so they can switch characters
| Do you have any obstacles? | Not common to use inheritance in Unity, so there arn't that many good tutorials about using inheritance in Unity. | The tutorials might use a different theory of how they jump and walk, than my own programs. | Very unfamiliar with Collectors as they are invisible in games, and therefore don't have a lot of exposre to how they work. | The codes that the tutorials use is complicated, so it will take me a while to understand it | Complicated scene management going on. That is very hard to understand.
Sprint 3 | What did you do yesterday? | Added the home and menu buttons. | Added the smart enemy after fustrating bug fixes.
| What will you work on today? | Add the smart enemies that use AI to find and follow the user. While avoiding obstacles. | Add inheritance to enemies and players, and improve quailty of life in the game
| Do you have any obstacles? | Very complicated, and AI has a bad reputation for being very hard. | Know the basics of inheritance, but still need to experiement on it, as the tutorials don't cover that much

## By Questions
Question | Person | Week: <date>
|  | Monday | Tuesday | Wednesday | Thursday | Friday
What did you do yesterday? | Jane
Alex
Jessica
What will you work on today? | Jane
Alex
Jessica
Do you have any obstacles? | Jane
Alex
Jessica